## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Lab 1
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Lee Xuan Hua | Foo Zhi Kai | Dario Ang | Alwin Chai | Fabrianne Effendi | Wong Li Han | Yam Hui Jing
Team member's mood during the this week's meeting: |  |  | Happy | Happy | Happy | Happy | Happy | Happy | Happy
1 | Complete Use Case Document | Task Quality Evaluation (After Task Completed) | 10 |  | 10 | 10 |  | 10 |  | 9 | 5 | 5.25 | Lee Xuan Hua Dario Ang Alwin Chai Wong Li Han | Lee Xuan Hua Dario Ang Alwin Chai Wong Li Han | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  | 9 |  | 9 | 9 |  | 9
| Estimated Task Difficulty（0-10） |  | 5 |  | 5 | 5 |  | 5
| Estimated Time Required for the Task（1-14 Days） |  | 5 |  | 5 | 5 |  | 6
| Team Member's Confidence about the Task (0-10) |  | 7 |  | 7 | 7 |  | 7
2 | Complete Project Proposal Document | Task Quality Evaluation (After Task Completed) |  | 10 |  |  | 10 |  | 10 | 9 | 5 | 6 | Foo Zhi Kai Fabrianne Effendi Yam Hui Jing | Foo Zhi Kai Fabrianne Effendi Yam Hui Jing | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  |  | 9 |  |  | 9 |  | 9
| Estimated Task Difficulty（0-10） |  |  | 5 |  |  | 5 |  | 5
| Estimated Time Required for the Task（1-14 Days） |  |  | 6 |  |  | 6 |  | 6
| Team Member's Confidence about the Task (0-10) |  |  | 8 |  |  | 8 |  | 8
3 | Exploration of Use Case Feasibility (if use case need further amendments) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 5 | 2 | Lee Xuan Hua Foo Zhi Kai Dario Ang Alwin Chai Fabrianne Effendi Wong Li Han Yam Hui Jing | Lee Xuan Hua Foo Zhi Kai Dario Ang Alwin Chai Fabrianne Effendi Wong Li Han Yam Hui Jing | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  | 7 | 7 | 7 | 7 | 7 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
4 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
5 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
6 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
7 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
8 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
9 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
10 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)

## Lab 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Lee Xuan Hua | Foo Zhi Kai | Dario Ang | Alwin Chai | Fabrianne Effendi | Wong Li Han | Yam Hui Jing
Team member's mood during the this week's meeting:
1 | Software Requirements Specification (SRS) | Task Quality Evaluation (After Task Completed) | 10 |  |  | 10 | 10 | 10 | 10 | 9 | 5 | 5.2 | Lee Xuan Hua Fabrianne Effendi Alwin Chai Wong Li Han Yam Hui Jing | Lee Xuan Hua Fabrianne Effendi Alwin Chai Wong Li Han Yam Hui Jing | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  | 9 |  |  | 9 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 5 |  |  | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 5 |  |  | 5 | 5 | 6 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 |  |  | 7 | 7 | 7 | 7
2 | Writing Quality Plan | Task Quality Evaluation (After Task Completed) |  | 10 | 10 |  |  |  |  | 9 | 5 | 6 | Foo Zhi Kai Dario Ang | Foo Zhi Kai Dario Ang Wong Li Han Lee Xuan Hua | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  |  | 9 | 9
| Estimated Task Difficulty（0-10） |  |  | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  |  | 6 | 6
| Team Member's Confidence about the Task (0-10) |  |  | 8 | 8
3 | Setting Up Database & Frontend | Task Quality Evaluation (After Task Completed) | 10 | 10 |  |  |  | 10 | 10 | 7 | 5 | 2 | Lee Xuan Hua Foo Zhi Kai Wong Li Han Yam Hui Jing | Lee Xuan Hua Foo Zhi Kai Wong Li Han Yam Hui Jing | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  | 7 | 7 |  |  |  | 7 | 7
| Estimated Task Difficulty（0-10） |  | 5 | 5 |  |  |  | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 |  |  |  | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 |  |  |  | 8 | 8
4 | Finetuning Machine Learning Models | Task Quality Evaluation (After Task Completed) |  |  | 10 | 10 | 10 |  |  | 7 | 5 | 2 | Dario Ang Alwin Chai Fabrianne Effendi | Dario Ang Alwin Chai Fabrianne Effendi | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  |  |  | 7 | 7 | 7
| Estimated Task Difficulty（0-10） |  |  |  | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  |  |  | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  |  |  | 8 | 8 | 8
5 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
6 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
7 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
8 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
9 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
10 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)

## Lab 3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Lee Xuan Hua | Foo Zhi Kai | Dario Ang | Alwin Chai | Fabrianne Effendi | Wong Li Han | Yam Hui Jing
Team member's mood during the this week's meeting:
1 | Project Plan | Task Quality Evaluation (After Task Completed) |  |  | 10 | 10 |  | 10 | 10 | 9 | 5 | 5.25 | Dario Ang Alwin Chai Wong Li Han Yam Hui Jing | Dario Ang Alwin Chai Wong Li Han Yam Hui Jing | Through Discussion | Yes | 5 | Happy | 10
| Estimated Task Priority（0-10） |  |  |  | 9 | 9 |  | 9 | 9
| Estimated Task Difficulty（0-10） |  |  |  | 5 | 5 |  | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  |  |  | 5 | 5 |  | 6 | 5
| Team Member's Confidence about the Task (0-10) |  |  |  | 7 | 7 |  | 7 | 7
2 | Risk Management | Task Quality Evaluation (After Task Completed) |  | 10 |  |  | 10 |  |  | 9 | 5 | 6 | Foo Zhi Kai Fabrianne Effendi | Foo Zhi Kai Fabrianne Effendi | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  |  | 9 |  |  | 9
| Estimated Task Difficulty（0-10） |  |  | 5 |  |  | 5
| Estimated Time Required for the Task（1-14 Days） |  |  | 6 |  |  | 6
| Team Member's Confidence about the Task (0-10) |  |  | 8 |  |  | 8
3 | Coding for User Application | Task Quality Evaluation (After Task Completed) | 10 |  | 10 |  | 10 |  |  | 10 | 7 | 7 | Lee Xuan Hua Dario Ang Fabrianne Effendi | Lee Xuan Hua Dario Ang Fabrianne Effendi | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 |  | 10 |  | 10
| Estimated Task Difficulty（0-10） |  | 7 |  | 7 |  | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 |  | 7 |  | 7
| Team Member's Confidence about the Task (0-10) |  | 8 |  | 8 |  | 8
4 | Coding for Invigilator Website | Task Quality Evaluation (After Task Completed) |  |  |  | 10 |  | 10 | 10 | 10 | 7 | 7 | Foo Zhi Kai Wong Li Han Yam Hui Jing | Foo Zhi Kai Wong Li Han Yam Hui Jing | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  |  |  |  | 10 |  | 10 | 10
| Estimated Task Difficulty（0-10） |  |  |  |  | 7 |  | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  |  |  |  | 7 |  | 7 | 7
| Team Member's Confidence about the Task (0-10) |  |  |  |  | 8 |  | 8 | 8
5 | Demo Prepation and Script | Task Quality Evaluation (After Task Completed) |  | 10 | 10 |  | 10 |  | 10 | 8 | 5 | 4 | Foo Zhi Kai Dario Ang Yam Hui Jing Fabrianne Effendi | Foo Zhi Kai Dario Ang Yam Hui Jing Fabrianne Effendi | Through Discussion | Yes | 5 | Happy | 10
| Estimated Task Priority（0-10） |  |  | 8 | 8 |  | 8 |  | 8
| Estimated Task Difficulty（0-10） |  |  | 5 | 5 |  | 5 |  | 5
| Estimated Time Required for the Task（1-14 Days） |  |  | 4 | 4 |  | 4 |  | 4
| Team Member's Confidence about the Task (0-10) |  |  | 8 | 8 |  | 8 |  | 8
6 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
7 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
8 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
9 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
10 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)

## Template
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Name1 | Name2 | Name3 | Name4 | Name5 | Name6 | Name7
Team member's mood during the this week's meeting: |  |  | Neutral | Neutral | Neutral | Neutral | Neutral | Neutral | Neutral
1 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
2 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
3 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
4 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
5 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
6 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
7 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
8 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
9 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)
10 |  | Task Quality Evaluation (After Task Completed) | [7 empty] | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0!
Estimated Task Priority（0-10）
Estimated Task Difficulty（0-10）
Estimated Time Required for the Task（1-14 Days）
Team Member's Confidence about the Task (0-10)